## Slide 1: Getting Started
Complete the Engagement Sizing Survey.
Collect relevant inputs.
Determine workshop participants & date.
Send invites, to include pre-work.

## Slide 2: STOP!!
All process need the following (regardless of doing which workshops being conducted):
Mission & Vision
Strategic Goals & 2024 OKRs (or priorities)
AI Vision: How will AI enable you to multiply your mission?
AI Guiding Principles

## Slide 3
Kickoff & Discovery
Sizing & Scoping AI Transformation

## Slide 4: Setting the Size & Scope
Setting Expectations |  |  |  |  | 
Expected Outcomes (fix, accomplish, avoid) | Fix lagging performance | Find efficiencies to shift time to strategic work | Reinvent our value proposition | Find a new product or service | Notes:
Known Guardrails | Existing privacy, data, etc. policies | Legal Team Direction | Budget Caps | Other: | 
Current AI Exploration | Watching & reading | Happening organically in organization | Active projects | Other: | 
Setting Process Parameters |  |  |  |  | 
Degree of Process | Lightweight | Medium | Comprehensive | Other: | 
Involved in Process | Exec Team | Select Departments | All Departments | Other: | 
Approach to AI Strategy | Integrated into current plans | Stand alone strategy | Other: |  | 
Existing Plans | Mission, Vision, Values | Competitive Strategy | Strategic Goals | 2024 OKRs | 
Additional Materials | Additional Documents or Plans to include: |  |  |  | 
Instructions: Turn responses bold or red.
Could be a JotForm

## Slide 5: Expected Outcomes
Outcomes:
From the survey
Strategic Issues to Address:
What problems are we solving?
What other outcomes do you want to see as part of this process?

## Slide 6: Design Principles
Planning Team’s role is building the plan; Board’s role is confirming & refining.
New plan will be directional in nature, less tactical/operational.
Using the current plan to see what we’ve learned, what’s still relevant, & what can be carried forward.
Planning session will be organized by strategic topic to rapidly cascade to org-wide goals, KPIs, & initiatives.
Simplifying performance management but keeping monthly meeting cadence.
Building the strategic planning and decision-making muscle for Leadership team.

## Slide 7: Plan Elements
Planning Element | Current | Expectation (Overhaul, Needs Refinement, Complete)
Mission |  | 
Vision |  | 
Values |  | 
SWOT |  | 
Competitive Advantages |  | 
Strategic Goals |  | 
<YEAR> OKRs |  | 

## Slide 8: Planning Team
Role | WHO? | Responsibilities
Strategy Champion |  | Final decision maker
Strategy Leader |  | Owns the planning process and execution cycle
Project Team |  | 
Planning Team |  | 
OnStrategy Team |  | 
Notes: Bios
Erica: https://onstrategyhq.com/about-us/team/erica-olsen/
Kim: https://onstrategyhq.com/about-us/team/kim-perkins/

## Slide 9: Plan Structure
Level |  | Planning Element & Definition | Accountability/Owner | Frequency of Modification
1 | What (overall) | Strategic Priorities | N/A | 3+ years
1.1 | What (this year) | Goals Outcomes & Strategies | Executive Leadership | 1-3 years
1.1.1 | How | Key Performance Indicators and/or Initiatives |  | 1 year (w/ qrtly targets)
1.1.1.1 |  | Action Items |  | Quarterly/Monthly

## Slide 10
AI Vision & Strategy Vision, Guiding Principles, & Governance
Establish Your Organization’s Stance & Guiding Approach to AI

## Slide 11
Workshop
Overview
Participants: Execs
Duration: 2 hrs.
Prep Work:
Org Strategy
2023 Goal Performance
Existing policies
Pre-thinking questions
Workshop Flow
Confirm Company Direction Recap organizational purpose, values, vision & winning strategy.
Develop AI Vision
Develop AI Guiding Principles Developed AI Guiding Principles, supporting policies to include approved tools.
Agree on a Governance Approach Agreed upon governance approach, structure, & executive champion.
Agree on a Training & Learning Approach Set approach to training & continuous learning.
Determine Rollout & Communication Organizational rollout & continuous communication.
Deliverables
Your Company’s AI Playbook
Notes: JEFF

## Slide 12: Creating your AI Guiding Principles
Your Existing Material
Company Values
Current Policies (GDPR, CCPA, etc.)
Legal Guidance
OTHER
Examples for Inspiration
See next slides
ChatGPT Prompts
HERE
Purpose: To create behavioral statements that everyone is expected to adhere to.
Instructions:
Create the Outline. Determine the topics that need a principle.
Audit the Outline. Look at the current policies to determine if all topics are covered.
Draft the Guiding Principles.
Determine which GPs need detailed policies.
Determine which AI Tools support the GPs.
Finalize via a legal and executive review.

## Slide 13: Creating your AI Guiding Principles – Part 1
Topic | Guiding Principle? | Detailed Policy?
Data Quality & Privacy- Manage your proprietary & customer data |  | 
Impact on Jobs – Stance on displacement |  | 
Equity & Discrimination - Controls to mitigate bias |  | 
Accountability – Expect behavioral compliance |  | 
Inaccuracy, Plagiarism – Addressing misappropriation |  | 
Security – Any changes to current security stance |  | 
Transparency – Ability to inspect all aspects and facts related to your AI models |  | 
Remediation - Mitigate risks & proactive risk response |  | 

## Slide 14: Creating your AI Guiding Principles – Part 2
 | Topic | Guiding Principle | Rationale & Support
1. |  |  | 
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 

## Slide 15
Transformative AI – Product/Services Create a brand-new value proposition
Y

## Slide 16
Workshop
Overview
Participants:
Duration:
Prep Work:
Workshop Flow
Focus Areas for Ideation Setting guardrails and fueling thinking
Forms of Innovation Leveraging what’s available and creating new
Problems We’ll Solve Innovation with a purpose
Customer Journey Shifts to own the customer journey
Building an AI Action Plan Moving forward
Deliverables
Your Company’s AI Product & Service Transformation Playbook

## Slide 17: Building the Action Plan
AI Solve: |  |  | 
Champion: |  | Dream Team: (SMEs, Key People) | 
GTM Target: Year 1/ 2/ 3 of plan |  | Value creation: S / M / L / XL | 
Rationale: |  |  | 
AI to: (Select all that apply) Research / Build / Perform |  | Level: (Select one) Reuse / Recombination / Novel | 
Data We Have: |  | Data We Need: | 
Current Capabilities: |  | Adds or Shifts Required: | 
Milestones: |  |  | 
Notes: Ideation – Not sure about workspace
Create 1 grid per AI Solve
Champion
Rationale
Data We Have Limit for now to sources or categories – level of details and volume available for training will take them time to clarify
Data We Need Sources or categories… Knowing _____ would be a game changer
GTM Target is estimated Year 1/2/3 of the plan
Shifts:
May be cultural, current legal position, talent available in house …. Something will have to change – what? Name the elephants in the room

## Slide 18
<Client Name> GenAI Playbook
As of <date>

## Slide 19
[Company Name] Strategy Summary

## Slide 20
[Company Name] GenAI Strategy Summary
TO BE BUILT LAST

## Slide 21: AI Vision & Strategy Where are we going?
<AI Vision>
1
3
2
STRATEGY #1
<STATEMENT>
STRATEGY #2
<STATEMENT>
STRATEGY #3
<STATEMENT>

## Slide 22: AI Guiding Principles
What guides our decision-making and approach?
Principle #1
Complete perspective from Executives, Directors, Managers & Staff. Conduct competitive analysis and customer research (optional).
Principle #2
Complete perspective from Executives, Directors, Managers & Staff. Conduct competitive analysis and customer research (optional)
Principle #3
Complete perspective from Executives, Directors, Managers & Staff. Conduct competitive analysis and customer research (optional).
Principle #4
Complete perspective from Executives, Directors, Managers & Staff. Conduct competitive analysis and customer research (optional).
Principle #5
Complete perspective from Executives, Directors, Managers & Staff. Conduct competitive analysis and customer research (optional).

## Slide 23: AI Policy

## Slide 24: Approved Tools
TOOL
<Use case>
TOOL
<Use case>
TOOL
<Use case>
TOOL
<Use case>