## Sheet1
Express Upgrades
[22 empty] | DATE: | 2017-12-06
Lake Castleton
[22 empty] | Revision # |  | 5
SEQUENCING OF UNITS
[12 empty] | ACTUAL COSTS |  |  |  |  | COMPARISON |  |  |  | VARIANCES
|  | Renovate Week Of | Building | Unit | Address | Unit Name | Washer/Dryer Plan | Upgrade Level | NOTES | Projected Turn Over | Actual Turn Over | Contract Amount | Change Order Amount | Permit/Inspection Fees | Total Reno Costs | Appliances | Budget Reno Costs | Budget Appliances | Budget Reno Costs to Actual (OVER) | Budget Appliance Costs to Actual (OVER) | Total Budget | Actual | $'s Diff (OVER) | % Diff (OVER)
1 |  |  | 63 | 848 | 7801 B Carlton Arms Rd #0848 | Congressional II | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 5954 | 1056 | 1017 | 8027 | 1930 | 7058 | 2090 | -969 | 160 | 9148 | 9957 | -809 | -8.8435
2 |  |  | 86 | 1217 | 7065 C Patrick Place #1217 | Patriot | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8095 | 735 | 1018 | 9848 | 1930 | 9198 | 1862 | -650 | -68 | 11060 | 11778 | -718 | -6.4919
3 |  |  | 17 | 231 | 7162 A American Way #0231 | Constitution | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-14 | 8106 | 431 | 1018 | 9555 | 1773 | 9210 | 1862 | -345 | 89 | 11072 | 11328 | -256 | -2.3121
4 |  |  | 73 | 1000 | 7874 F Musket Street #1000 | Declaration | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 7891 | 270 | 1018 | 9179 | 1930 | 8940 | 1862 | -239 | -68 | 10802 | 11109 | -307 | -2.8421
5 |  |  | 56 | 752 | 7779 B Newport Way #0752 | Washington II | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-14 | 7519 | 759 | 1018 | 9296 | 1773 | 8622 | 1862 | -674 | 89 | 10484 | 11069 | -585 | -5.5799
6 |  |  | 59 | 785 | 7124 C Old House Rd #0785 | Gettysburg | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8027 | 84 | 1018 | 9129 | 1773 | 9130 | 1862 | 1 | 89 | 10992 | 10902 | 90 | 0.81878
7 |  |  | 80 | 1107 | 7125 A Caisson Street #1107 | Hancock | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 7179 | 84 | 1018 | 8281 | 1773 | 8605 | 1862 | 324 | 89 | 10467 | 10054 | 413 | 3.9457
8 |  |  | 84 | 1182 | 7028 Patrick Place #1182 | Carlton | Existing W/D in unit | A | Leased but not occupied | 2017-11-10 | 2017-11-14 | 8385 | 188 | 1018 | 9591 | 1773 | 6416 | 1151 | -3175 | -622 | 7567 | 11364 | -3797 | -50.1784
9 |  |  | 36 | 498 | 7538 Carlton Arms Rd #0498 | Madison | Add app. only | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8198 | 416 | 1018 | 9632 | 1773 | 6134 | 1862 | -3498 | 89 | 7996 | 11405 | -3409 | -42.6338
10 |  |  | 57 | 759 | 7759 A Newport Way #0759 | Presidential | Add app. only | A | Occupied | 2017-11-10 | 2017-11-15 | 8721 | 262 | 1018 | 10001 | 1773 | 6326 | 1862 | -3675 | 89 | 8188 | 11774 | -3586 | -43.7958
11 |  |  | 10 | 122 | 7029 D Old House Rd #0122 | Harrison II | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 7484 | 377 | 1018 | 8879 | 1773 | 8588 | 1862 | -291 | 89 | 10450 | 10652 | -202 | -1.933
12 |  |  | 12 | 133 | 7039 C American Way #0133 | Independence | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8095 | 1395 | 1018 | 10508 | 1773 | 9198 | 1862 | -1310 | 89 | 11060 | 12281 | -1221 | -11.0398
13 |  |  | 70 | 962 | 7824 D Musket St #0962 | Presidential | Existing W/D in unit | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8724 | 771 | 1018 | 10513 | 1773 | 6326 | 1151 | -4187 | -622 | 7477 | 12286 | -4809 | -64.3172
14 |  |  | 49 | 634 | 7811 D Carlton Arms Dr #0634 | Liberty | Add conn. & app. | A | Occupied | 2017-11-10 | 2017-12-07 | 9684 | 204 | 1018 | 10906 | 1930 | 10788 | 2321 | -118 | 391 | 13109 | 12836 | 273 | 2.0825
15 |  |  | 37 | 506 | 7514 D carlton Arms Rd#506 | Lincoln | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-14 | 7172 | 0 | 1018 | 8190 | 1773 | 8275 | 1862 | 85 | 89 | 10137 | 9963 | 174 | 1.7165
16 |  |  | 69 | 946 | 7812 B Musket St #0946 | Congressional II | Add conn. & app. | A | Occupied | 2017-11-10 | 2017-11-14 | 5954 | 435 | 1018 | 7407 | 1930 | 7058 | 2090 | -349 | 160 | 9148 | 9337 | -189 | -2.066
17 |  |  | 3 | 17 | 7632 C Carlton Arms Dr #0017 | Harrison II | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 7484 | 231 | 1018 | 8733 | 1773 | 8588 | 1862 | -145 | 89 | 10450 | 10506 | -56 | -0.53589
18 |  |  | 27 | 363 | 7149 A Whitestone Rd #0363 | Constitution | Add conn. & app. | A | Vacant Unit | 2017-11-10 | 2017-11-15 | 8106 | 541 | 1018 | 9665 | 1773 | 4710 | 1862 | -4955 | 89 | 6572 | 11438 | -4866 | -74.0414
19 |  |  | PHASE I ROLLOUT
20 | 1 | 2017-12-04 | 49 | 631 | 7811 A Carlton Arms Dr #0631 | Hancock II | Add conn. & app. | A | Unoccupied/new toilet | 2017-12-07 | 2017-12-07 | 7543.65 |  | 0 |  | 1774.06 | 7543.65 | 1774.06 | 7543.65 | 0 | 9317.71 | 1774.06 | 7543.65 | 80.9603
21 | 2 | 2017-12-04 | 49 | 632 | 7811 B Carlton Arms Dr #0632 | Liberty | Add app. only | A | Existing W/D Connect | 2017-12-08 | 2017-12-08 | 10048.65 |  | 0 |  | 1929.213 | 10048.65 | 1929.213 | 10048.65 | 0 | 11977.863 | 1929.213 | 10048.65 | 83.8935
22 | 3 | 2017-12-04 | 49 | 633 | 7811 C Carlton Arms Dr #0633 | Hancock II | Add conn. & app. | A | Unoccupied/ceramic tile | 2017-12-08 | 2017-12-08 | 7543.65 |  | 0 |  | 1774.06 | 7543.65 | 1774.06 | 7543.65 | 0 | 9317.71 | 1774.06 | 7543.65 | 80.9603
23 | 4 | 2017-12-04 | 49 | 635 | 7817 A Carlton Arms Dr #0635 | Hancock II | Add conn. & app. | A |  | 2017-12-08 | 2017-12-08 | 7543.65 |  | 0 |  | 1774.06 | 7543.65 | 1774.06 | 7543.65 | 0 | 9317.71 | 1774.06 | 7543.65 | 80.9603
24 | 5 | 2017-12-04 | 49 | 636 | 7817 B Carlton Arms Dr #0636 | Lincoln | Add conn. & app. | A | Unoccupied | 2017-12-07 | 2017-12-07 | 7536.65 |  | 0 |  | 1774.06 | 7536.65 | 1774.06 | 7536.65 | 0 | 9310.71 | 1774.06 | 7536.65 | 80.946
25 | 6 | 2017-12-04 | 49 | 638 | 7817 D Carlton Arms Dr #0638 | Lincoln | Add conn. & app. | A | New garbage disposal | 2017-12-07 | 2017-12-07 | 7536.65 |  | 0 |  | 1774.06 | 7536.65 | 1774.06 | 7536.65 | 0 | 9310.71 | 1774.06 | 7536.65 | 80.946
26 | 7 | 2017-12-04 | 49 | 639 | 7823 A Carlton Arms Dr #0639 | Liberty | Add conn. & app. | A |  | 2017-12-08 | 2017-12-08 | 10048.65 |  | 0 |  | 1929.213 | 10048.65 | 1929.213 | 10048.65 | 0 | 11977.863 | 1929.213 | 10048.65 | 83.8935
27 | 8 | 2017-12-04 | 49 | 640 | 7823 B Carlton Arms Dr #0640 | Hancock II | Add conn. & app. | A |  | 2017-12-07 | 2017-12-07 | 7543.65 |  | 0 |  | 1774.06 | 7543.65 | 1774.06 | 7543.65 | 0 | 9317.71 | 1774.06 | 7543.65 | 80.9603
28 | 9 | 2017-12-04 | 49 | 641 | 7823 C Carlton Arms Dr #0641 | Liberty | Add conn. & app. | A | Newe layout W/D | 2017-12-08 | 2017-12-08 | 10048.65 |  | 0 |  | 1929.213 | 10048.65 | 1929.213 | 10048.65 | 0 | 11977.863 | 1929.213 | 10048.65 | 83.8935
29 | 10 | 2017-12-04 | 49 | 642 | 7823 D Carlton Arms Dr #0642 | Hancock II | Add conn. & app. | A | New garbage disposal | 2017-12-07 | 2017-12-07 | 7543.65 |  | 0 |  | 1774.06 | 7543.65 | 1774.06 | 7543.65 | 0 | 9317.71 | 1774.06 | 7543.65 | 80.9603
30 | 11 | 2017-12-04 | 54 | 707 | 7778 A Newport Way #0707 | Harrison II | Add conn. & app. | A |  | 2017-12-08 | 2017-12-08 | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
31 | 12 | 2017-12-04 | 54 | 708 | 7778 B Newport Way #0708 | Harrison II | Add conn. & app. | A |  | 2017-12-08 | 2017-12-08 | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
32
33 | 1 | 2017-12-11 | 54 | 709 | 7778 C Newport Way #0709 | Harrison II | Add conn. & app. | A |  | 2017-12-11 |  | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
34 | 2 | 2017-12-11 | 54 | 710 | 7778 D Newport Way #0710 | Harrison II | Add conn. & app. | A |  | 2017-12-11 |  | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
35 | 3 | 2017-12-11 | 54 | 712 | 7782 B Newport Way #0712 | Congressional II | Add conn. & app. | A |  | 2017-12-12 |  | 6318.65 |  | 0 |  | 1698.09 | 6318.65 | 1698.09 | 6318.65 | 0 | 8016.74 | 1698.09 | 6318.65 | 78.8182
36 | 4 | 2017-12-11 | 54 | 713 | 7782 C Newport Way #0713 | Declaration | Add conn. & app. | A |  | 2017-12-11 |  | 8201.65 |  | 0 |  | 1929.21 | 8201.65 | 1929.21 | 8201.65 | 0 | 10130.86 | 1929.21 | 8201.65 | 80.9571
37 | 5 | 2017-12-11 | 54 | 715 | 7782 E Newport Way #0715 | Congressional II | Add conn. & app. | A |  | 2017-12-12 |  | 6318.65 |  | 0 |  | 1698.09 | 6318.65 | 1698.09 | 6318.65 | 0 | 8016.74 | 1698.09 | 6318.65 | 78.8182
38 | 6 | 2017-12-11 | 54 | 716 | 7782 F Newport Way #0716 | Declaration | Add conn. & app. | A |  | 2017-12-11 |  | 8201.65 |  | 0 |  | 1929.21 | 8201.65 | 1929.21 | 8201.65 | 0 | 10130.86 | 1929.21 | 8201.65 | 80.9571
39 | 7 | 2017-12-11 | 54 | 717 | 7786 A Newport Way #0717 | Declaration | Add conn. & app. | A |  | 2017-12-11 |  | 8201.65 |  | 0 |  | 1929.21 | 8201.65 | 1929.21 | 8201.65 | 0 | 10130.86 | 1929.21 | 8201.65 | 80.9571
40 | 8 | 2017-12-11 | 54 | 718 | 7786 B Newport Way #0718 | Congressional II | Add conn. & app. | A |  | 2017-12-12 |  | 6318.65 |  | 0 |  | 1698.09 | 6318.65 | 1698.09 | 6318.65 | 0 | 8016.74 | 1698.09 | 6318.65 | 78.8182
41 | 9 | 2017-12-11 | 54 | 720 | 7786 D Newport Way #0720 | Declaration | Add conn. & app. | A |  | 2017-12-11 |  | 8201.65 |  | 0 |  | 1929.21 | 8201.65 | 1929.21 | 8201.65 | 0 | 10130.86 | 1929.21 | 8201.65 | 80.9571
42 | 10 | 2017-12-11 | 54 | 721 | 7786 E Newport Way #0721 | Congressional II | Add conn. & app. | A |  | 2017-12-12 |  | 6318.65 |  | 0 |  | 1698.09 | 6318.65 | 1698.09 | 6318.65 | 0 | 8016.74 | 1698.09 | 6318.65 | 78.8182
43 | 11 | 2017-12-11 | 54 | 723 | 7790 A Newport Way #0723 | Harrison II | Add conn. & app. | A |  | 2017-12-12 |  | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
44 | 12 | 2017-12-11 | 54 | 724 | 7790 B Newport Way #0724 | Harrison II | Add conn. & app. | A |  | 2017-12-12 |  | 7848.65 |  | 0 |  | 1774.06 | 7848.65 | 1774.06 | 7848.65 | 0 | 9622.71 | 1774.06 | 7848.65 | 81.5638
45
46 | 1 | 2017-12-18 | 54 | 725 | 7790 C Newport Way #0725 | Harrison II | Add conn. & app. | A | [8 empty] | 7848.65 | 1774.06 | 7848.65 | 1774.06 | 9622.71 | 0 | 9622.71 | 100
47 | 2 | 2017-12-18 | 54 | 726 | 7790 D Newport Way #0726 | Harrison II | Add conn. & app. | A | [8 empty] | 7848.65 | 1774.06 | 7848.65 | 1774.06 | 9622.71 | 0 | 9622.71 | 100
48 |  | 2017-12-11 | 55 | 729 | 7783 C Newport Way #0729 | Congressional I | Add conn. & app. | A | Misslabeled | [7 empty] | 6318.65 | 1698.09 | 6318.65 | 1698.09 | 8016.74 | 0 | 8016.74 | 100
49 |  | 2017-12-11 | 55 | 733 | 7783 G Newport Way #0733 | Congressional I | Add conn. & app. | A | Misslabeled | [7 empty] | 6318.65 | 1698.09 | 6318.65 | 1698.09 | 8016.74 | 0 | 8016.74 | 100
50 |  | 2017-12-11 | 55 | 736 | 7787 B Newport Way #0736 | Congressional I | Add conn. & app. | A | Misslabeled | [7 empty] | 6318.65 | 1698.09 | 6318.65 | 1698.09 | 8016.74 | 0 | 8016.74 | 100
51 |  | 2017-12-11 | 55 | 740 | 7787 F Newport Way #0740 | Congressional I | Add conn. & app. | A | Misslabeled | [7 empty] | 6318.65 | 1698.09 | 6318.65 | 1698.09 | 8016.74 | 0 | 8016.74 | 100
52 | 3 | 2017-12-18 | 53 | 696 | 7762 B Newport Way #0696 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
53 | 4 | 2017-12-18 | 53 | 697 | 7762 C Newport Way #0697 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
54 | 5 | 2017-12-18 | 53 | 698 | 7762 D Newport Way #0698 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
55 | 6 | 2017-12-18 | 53 | 699 | 7766 A Newport Way #0699 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
56 | 7 | 2017-12-18 | 53 | 700 | 7766 B Newport Way #0700 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
57 | 8 | 2017-12-18 | 53 | 701 | 7766 C Newport Way #0701 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
58 | 9 | 2017-12-18 | 53 | 702 | 7766 D Newport Way #0702 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
59 | 10 | 2017-12-18 | 53 | 703 | 7770 A Newport Way #0703 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
60 | 11 | 2017-12-18 | 53 | 704 | 7770 B Newport Way #0704 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
61 | 12 | 2017-12-18 | 53 | 705 | 7770 C Newport Way #0705 | Constitution | Add conn. & app. | A | [8 empty] | 8470.65 | 1774.06 | 8470.65 | 1774.06 | 10244.71 | 0 | 10244.71 | 100
62 |  |  | ADDED NEW SHOWER CURTAIN ROD FROM HERE DOW
63 | 1 | 2018-01-02 | 53 | 706 | 7770 D Newport Way #0706 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
64 | 2 | 2018-01-02 | 56 | 743 | 7771 A Newport Way #0743 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
65 | 3 | 2018-01-02 | 56 | 744 | 7771 B Newport Way #0744 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
66 | 4 | 2018-01-02 | 56 | 745 | 7771 C Newport Way #O745 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
67 | 5 | 2018-01-02 | 56 | 746 | 7771 D Newport Way #0746 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
68 | 6 | 2018-01-02 | 56 | 747 | 7775 A Newport Way #0747 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
69
70 | 1 | 2018-01-09 | 56 | 748 | 7775 B Newport Way #0748 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
71 | 2 | 2018-01-09 | 56 | 749 | 7775 C Newport Way #0749 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
72 | 3 | 2018-01-09 | 56 | 750 | 7775 D Newport Way #0750 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
73 | 4 | 2018-01-09 | 56 | 751 | 7779 A Newport Way #0751 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
74 | 5 | 2018-01-09 | 56 | 753 | 7779 C Newport Way #0753 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
75 | 6 | 2018-01-09 | 56 | 754 | 7779 D Newport Way #0754 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
76 | 7 | 2018-01-09 | 57 | 755 | 7755 A Newport Way #0755 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
77 | 8 | 2018-01-09 | 57 | 756 | 7755 B Newport Way #0756 | Presidential | Add conn. & app. | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
78 | 9 | 2018-01-09 | 57 | 757 | 7755 C Newport Way #0757 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
79 | 10 | 2018-01-09 | 57 | 758 | 7755 D Newport Way #0758 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
80 | 11 | 2018-01-09 | 57 | 760 | 7759 B Newport Way #0760 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
81 | 12 | 2018-01-09 | 57 | 761 | 7759 C Newport Way #0761 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
82
83 | 1 | 2018-01-15 | 57 | 762 | 7759 D Newport Way #0762 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
84 | 2 | 2018-01-15 | 57 | 763 | 7763 A Newport Way #0763 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
85 | 3 | 2018-01-15 | 57 | 764 | 7763 B Newport Way #0764 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
86 | 4 | 2018-01-15 | 57 | 765 | 7763 C Newport Way #0765 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
87 | 5 | 2018-01-15 | 57 | 766 | 7763 D Newport Way #0766 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
88 | 6 | 2018-01-15 | 57 | 767 | 7767 A Newport Way #0767 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
89 | 7 | 2018-01-15 | 57 | 768 | 7767 B Newport Way #0768 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
90 | 8 | 2018-01-15 | 57 | 769 | 7767 C Newport Way #0769 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
91 | 9 | 2018-01-15 | 57 | 770 | 7767 D Newport Way #0770 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
92 | 10 | 2018-01-15 | 58 | 771 | 7743 A Newport Way #0771 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
93 | 11 | 2018-01-15 | 58 | 772 | 7743 B Newport Way #0772 | Liberty | Add conn. & app. | A | Exist cabinets-good shape | [7 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
94 | 12 | 2018-01-15 | 58 | 773 | 7743 C Newport Way #0773 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
95 | 13 | 2018-01-15 | 58 | 774 | 7743 D Newport Way #0774 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
96 | 14 | 2018-01-15 | 58 | 775 | 7749 A Newport Way #0775 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
97 | 15 | 2018-01-15 | 58 | 776 | 7749 B Newport Way #0776 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
98 | 16 | 2018-01-15 | 58 | 778 | 7749 D Newport Way #0778 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
99
100 | 1 | 2018-01-22 | 59 | 779 | 7118 A Old House Rd #0779 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
101 | 2 | 2018-01-22 | 59 | 780 | 7118 B Old House Rd #0780 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
102 | 3 | 2018-01-22 | 59 | 781 | 7118 C Old House Rd #0781 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
103 | 4 | 2018-01-22 | 59 | 782 | 7118 D Old House Rd #0782 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
104 | 5 | 2018-01-22 | 59 | 783 | 7124 A Old House Rd #0783 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
105 | 6 | 2018-01-22 | 59 | 784 | 7124 B Old House Rd #0784 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
106 | 7 | 2018-01-22 | 59 | 786 | 7124 D Old House Rd #0786 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
107 | 8 | 2018-01-22 | 59 | 787 | 7130 A Old House Rd #0787 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
108 | 9 | 2018-01-22 | 59 | 788 | 7130 B Old House Rd #0788 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
109 | 10 | 2018-01-22 | 59 | 789 | 7130 C Old House Rd #0789 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
110 | 11 | 2018-01-22 | 59 | 790 | 7130 D Old House Rd #0790 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
111 | 12 | 2018-01-22 | 59 | 791 | 7136 A Old House Rd #0791 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
112 | 13 | 2018-01-22 | 59 | 792 | 7136 B Old House Rd #0792 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
113 | 14 | 2018-01-22 | 59 | 793 | 7136 C Old House Rd #0793 | Gettysburg | Add app. only | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
114 | 15 | 2018-01-22 | 59 | 794 | 7136 D Old House Rd #0794 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
115 | 16 | 2018-01-22 | 60 | 795 | 7740 A Carlton Arms Rd #0795 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
116
117 | 1 | 2018-01-29 | 60 | 796 | 7740 B Carlton Arms Rd #0796 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
118 | 2 | 2018-01-29 | 60 | 797 | 7740 C Carlton Arms Rd #0797 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
119 | 3 | 2018-01-29 | 60 | 798 | 7740 D Carlton Arms Rd #0798 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
120 | 4 | 2018-01-29 | 60 | 799 | 7746 A Carlton Arms Rd #0799 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
121 | 5 | 2018-01-29 | 60 | 801 | 7746 C Carlton Arms Rd #0801 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
122 | 6 | 2018-01-29 | 60 | 802 | 7746 D Carlton Arms Rd #0802 | Liberty | Existing W/D in unit | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
123 | 7 | 2018-01-29 | 61 | 803 | 7750 Carlton Arms Rd #0803 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
124 | 8 | 2018-01-29 | 61 | 804 | 7752 Carlton Arms Rd #0804 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
125 | 9 | 2018-01-29 | 61 | 805 | 7754 Carlton Arms Rd #0805 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
126 | 10 | 2018-01-29 | 61 | 806 | 7756 Carlton Arms Rd #0806 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
127 | 11 | 2018-01-29 | 61 | 807 | 7758 Carlton Arms Rd #0807 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
128 | 12 | 2018-01-29 | 61 | 808 | 7760 Carlton Arms Rd #0808 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
129 | 13 | 2018-01-29 | 61 | 809 | 7762 Carlton Arms Rd #0809 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
130 | 14 | 2018-01-29 | 61 | 810 | 7764 Carlton Arms Rd #0810 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
131 | 15 | 2018-01-29 | 61 | 811 | 7766 Carlton Arms Rd #0811 | Jefferson I | Add app. only | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
132 | 16 | 2018-01-29 | 61 | 812 | 7768 Carlton Arms Rd #0812 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
133
134 | 1 | 2018-02-05 | 49 | 634 | 7811 D Carlton Arms Dr #0634 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
135 |  |  | 49 | 637 | 7817 C Carlton Arms Dr #0637 | Hancock II | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
136 |  |  | 53 | 695 | 7762 A Newport Way #0695 | Constitution | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
137 |  |  | 58 | 777 | 7749 C Newport Way #0777 | Liberty | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
138 |  |  | 60 | 800 | 7746 B Carlton Arms Rd #0800 | Liberty | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
139 | 2 | 2018-02-05 | 61 | 813 | 7770 Carlton Arms Rd #0813 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
140 | 3 | 2018-02-05 | 61 | 814 | 7772 Carlton Arms Rd #0814 | Carlton | Add conn. & app. | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
141 | 4 | 2018-02-05 | 69 | 935 | 7804 A Musket St #0935 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
142 | 5 | 2018-02-05 | 69 | 936 | 7804 B Musket St #0936 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
143 | 6 | 2018-02-05 | 69 | 937 | 7804 C Musket St #0937 | Harrison II | Existing W/D in unit | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
144 | 7 | 2018-02-05 | 69 | 938 | 7804 D Musket St #0938 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
145 | 8 | 2018-02-05 | 69 | 941 | 7808 C Musket St #0941 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
146 | 9 | 2018-02-05 | 69 | 944 | 7808 F Musket St #0944 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
147 | 10 | 2018-02-05 | 69 | 945 | 7812 A Musket St #0945 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
148 | 11 | 2018-02-05 | 69 | 948 | 7812 D Musket St #0948 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
149 | 12 | 2018-02-05 | 69 | 951 | 7816 A Muskset St #0951 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
150 | 13 | 2018-02-05 | 69 | 952 | 7816 B Musket St #0952 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
151 | 14 | 2018-02-05 | 69 | 953 | 7816 C Musket St #0953 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
152 | 15 | 2018-02-05 | 69 | 954 | 7816 D Musket St #0954 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
153 | 16 | 2018-02-05 | 70 | 955 | 7820 A Musket St #0955 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
154
155 | 1 | 2018-02-12 | 70 | 956 | 7820 B Musket St #0956 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
156 | 2 | 2018-02-12 | 70 | 957 | 7820 C Musket #0957 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
157 | 3 | 2018-02-12 | 70 | 958 | 7820 D Musket St #0958 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
158 | 4 | 2018-02-12 | 70 | 959 | 7824 A Musket St #0959 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
159 | 5 | 2018-02-12 | 70 | 960 | 7824 B Musket St #0960 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
160 | 6 | 2018-02-12 | 70 | 961 | 7824 C Musket St #0961 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
161 | 7 | 2018-02-12 | 70 | 963 | 7828 A Musket St #0963 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
162 | 8 | 2018-02-12 | 70 | 964 | 7828 B Musket St #0964 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
163 | 9 | 2018-02-12 | 70 | 965 | 7828 C Musket St #0965 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
164 | 10 | 2018-02-12 | 70 | 966 | 7828 D Musket St #0966 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
165 | 11 | 2018-02-12 | 70 | 967 | 7832 A Musket St #0967 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
166 | 12 | 2018-02-12 | 70 | 968 | 7832 B Musket St #0968 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
167 | 13 | 2018-02-12 | 70 | 969 | 7832 C Musket St #969 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
168 | 14 | 2018-02-12 | 70 | 970 | 7832 D Musket St #0970 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
169 | 15 | 2018-02-12 | 71 | 971 | 7836 A Musket St #0971 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
170 | 16 | 2018-02-12 | 71 | 972 | 7836 B Musket St #0972 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
171
172 | 1 | 2018-02-19 | 71 | 973 | 7836 C Musket St #0973 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
173 | 2 | 2018-02-19 | 71 | 974 | 7836 D Musket St #0974 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
174 | 3 | 2018-02-19 | 71 | 975 | 7840 A Musket St #0975 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
175 | 4 | 2018-02-19 | 71 | 976 | 7840 B Musket St #0976 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
176 | 5 | 2018-02-19 | 71 | 977 | 7840 C Musket St. #0977 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
177 | 6 | 2018-02-19 | 71 | 978 | 7840 D Musket Street #0978 | Liberty | Existing W/D in unit | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
178 | 7 | 2018-02-19 | 72 | 979 | 7844 Musket Street #0979 | Madison | Add conn. & app. | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
179 | 8 | 2018-02-19 | 72 | 980 | 7846 Musket Street #0980 | Madison | Add conn. & app. | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
180 | 9 | 2018-02-19 | 72 | 981 | 7848 Musket Street #0981 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
181 | 10 | 2018-02-19 | 72 | 982 | 7850 Musket Street #0982 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
182 | 11 | 2018-02-19 | 72 | 983 | 7852 Musket Street #0983 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
183 | 12 | 2018-02-19 | 72 | 984 | 7854 Musket Street #0984 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
184 | 13 | 2018-02-19 | 72 | 985 | 7856 Musket Street #0985 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
185 | 14 | 2018-02-19 | 72 | 986 | 7858 Musket Street #0986 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
186 | 15 | 2018-02-19 | 72 | 987 | 7860 Musket Street #0987 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
187 | 16 | 2018-02-19 | 72 | 988 | 7862 Musket Street #0988 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
188 |  |  | 72 | 989 | 7864 Musket Street #0989 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
189 | 1 | 2018-02-26 | 72 | 990 | 7866 Musket Street #0990 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
190 | 2 | 2018-02-26 | 73 | 991 | 7870 A Musket Street #0991 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
191 | 3 | 2018-02-26 | 73 | 992 | 7870 B Musket Street #0992 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
192 | 4 | 2018-02-26 | 73 | 993 | 7870 C Musket Street #0993 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
193 | 5 | 2018-02-26 | 73 | 994 | 7870 D Musket Street #0994 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
194 | 6 | 2018-02-26 | 73 | 997 | 7874 C Musket Street #0997 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
195 | 7 | 2018-02-26 | 73 | 1001 | 7878 A Musket Street #1001 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
196 | 8 | 2018-02-26 | 73 | 1004 | 7878 D Musket Street #1004 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
197 |  |  | 73 | 1007 | 7882 A Musket Street #1007 | Harrison II | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
198 | 9 | 2018-02-26 | 73 | 1008 | 7882 B Musket Street #1008 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
199 | 10 | 2018-02-26 | 73 | 1009 | 7882 C Musket Street #1009 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
200 | 11 | 2018-02-26 | 73 | 1010 | 7882 D Musket Street #1010 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
201 | 12 | 2018-02-26 | 78 | 1079 | 7908 Carlton Arms Road #1079 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
202 | 13 | 2018-02-26 | 78 | 1080 | 7910 Carlton Arms Road #1080 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
203 | 14 | 2018-02-26 | 78 | 1081 | 7912 Carlton Arms Road #1081 | Jefferson I | Add app. only | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
204 |  |  | 78 | 1082 | 7914 Carlton Arms Road #1082 | Jefferson I | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
205 | 15 | 2018-02-26 | 78 | 1083 | 7916 Carlton Arms Road #1083 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
206 | 16 | 2018-02-26 | 78 | 1084 | 7918 Carlton Arms Road #1084 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
207
208 | 1 | 2018-03-05 | 78 | 1085 | 7920 Carlton Arms Rd #1085 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
209 | 2 | 2018-03-05 | 78 | 1086 | 7922 Carlton Arms Road #1086 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
210 | 3 | 2018-03-05 | 78 | 1087 | 7924 Carlton Arms Road #1087 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
211 | 4 | 2018-03-05 | 78 | 1088 | 7926 Carlton Arms Road #1088 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
212 | 5 | 2018-03-05 | 78 | 1089 | 7928 Carlton Arms Road #1089 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
213 | 6 | 2018-03-05 | 78 | 1090 | 7930 Carlton Arms Road #1090 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
214 | 7 | 2018-03-05 | 79 | 1091 | 7135 A Caisson Street #1091 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
215 | 8 | 2018-03-05 | 79 | 1092 | 7135 B Caisson Street #1092 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
216 | 9 | 2018-03-05 | 79 | 1093 | 7135 C Caisson Street #1093 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
217 | 10 | 2018-03-05 | 79 | 1094 | 7135 D Caisson Street #1094 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
218 | 11 | 2018-03-05 | 79 | 1095 | 7141 A Caisson Street #1095 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
219 | 12 | 2018-03-05 | 79 | 1096 | 7141 B Caisson Street #1096 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
220 | 13 | 2018-03-05 | 79 | 1097 | 7141 C Caisson Street #1097 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
221 | 14 | 2018-03-05 | 79 | 1098 | 7141 D Caisson St #1098 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
222 | 15 | 2018-03-05 | 80 | 1110 | 7125 D Caisson Street #1110 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
223 | 16 | 2018-03-05 | 86 | 1203 | 7047 A Patrick Place #1203 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
224
225 | 1 | 2018-03-12 | 86 | 1204 | 7047 B Patrick Place #1204 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
226 | 2 | 2018-03-12 | 86 | 1205 | 7047 C Patrick Place #1205 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
227 | 3 | 2018-03-12 | 86 | 1206 | 7047 D Patrick Place #1206 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
228 | 4 | 2018-03-12 | 86 | 1207 | 7053 A Patrick Place #1207 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
229 | 5 | 2018-03-12 | 86 | 1208 | 7053 B Patrick Place #1208 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
230 | 6 | 2018-03-12 | 86 | 1209 | 7053 C Patrick Place #1209 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
231 | 7 | 2018-03-12 | 86 | 1210 | 7053 D Patrick Place #1210 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
232 | 8 | 2018-03-12 | 86 | 1211 | 7059 A Patrick Place #1211 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
233 | 9 | 2018-03-12 | 86 | 1212 | 7059 B Patrick Place #1212 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
234 | 10 | 2018-03-12 | 86 | 1213 | 7059 C Patrick Place #1213 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
235 | 11 | 2018-03-12 | 86 | 1214 | 7059 D Patrick Place #1214 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
236 | 12 | 2018-03-12 | 86 | 1215 | 7065 A Patrick Place #1215 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
237 | 13 | 2018-03-12 | 86 | 1216 | 7065 B Patrick Place #1216 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
238 | 14 | 2018-03-12 | 86 | 1218 | 7065 D Patrick Place #1218 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
239 | 15 | 2018-03-12 | 87 | 1219 | 7037 A Patrick Place #1219 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
240 | 16 | 2018-03-12 | 87 | 1220 | 7037 B Patrick Place #1220 | Liberty | Existing W/D in unit | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
241
242 | 1 | 2018-03-19 | 87 | 1221 | 7037 C Patrick Place #1221 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
243 |  |  | 87 | 1222 | 7037 D Patrick Place #1222 | Liberty | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
244 | 2 | 2018-03-19 | 87 | 1223 | 7043 A Patrick Place #1223 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
245 | 3 | 2018-03-19 | 87 | 1224 | 7043 B Patrick Place #1224 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
246 | 4 | 2018-03-19 | 87 | 1225 | 7043 C Patrick Place #1225 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
247 | 5 | 2018-03-19 | 87 | 1226 | 7043 D Patrick Place #1226 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
248 | 6 | 2018-03-19 | 88 | 1227 | 7029 A Patrick Place #1227 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
249 | 7 | 2018-03-19 | 88 | 1228 | 7029 B Patrick Place #1228 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
250 | 8 | 2018-03-19 | 88 | 1229 | 7029 C Patrick Place #1229 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
251 | 9 | 2018-03-19 | 88 | 1230 | 7029 D Patrick Place #1230 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
252 | 10 | 2018-03-19 | 88 | 1231 | 7033 A Patrick Place #1231 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
253 | 11 | 2018-03-19 | 88 | 1232 | 7033 B Patrick Place #1232 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
254 | 12 | 2018-03-19 | 88 | 1233 | 7033 C Patrick Place #1233 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
255 | 13 | 2018-03-19 | 88 | 1234 | 7033 D Patrick Place #1234 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
256 | 14 | 2018-03-19 | 84 | 1171 | 7006 Patrick Place #1171 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
257 | 15 | 2018-03-19 | 84 | 1172 | 7008 Patrick Place #1172 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
258 | 16 | 2018-03-19 | 84 | 1173 | 7010 Patrick Place #1173 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
259
260 | 1 | 2018-03-26 | 84 | 1174 | 7012 Patrick Place #1174 | Jefferson I | Add app. only | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
261 | 2 | 2018-03-26 | 84 | 1175 | 7014 Patrick Place #1175 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
262 | 3 | 2018-03-26 | 84 | 1176 | 7016 Patrick Place #1176 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
263 | 4 | 2018-03-26 | 84 | 1177 | 7018 Patrick Place #1177 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
264 | 5 | 2018-03-26 | 84 | 1178 | 7020 Patrick Place #1178 | Carlton | Existing W/D in unit | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
265 | 6 | 2018-03-26 | 84 | 1179 | 7022 Patrick Place #1179 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
266 | 7 | 2018-03-26 | 84 | 1180 | 7024 Patrick Place #1180 | Jefferson I | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
267 | 8 | 2018-03-26 | 84 | 1181 | 7026 Patrick Place #1181 | Carlton | Add app. only | A | [8 empty] | 9000.83 | 1774.06 | 9000.83 | 1774.06 | 10774.89 | 0 | 10774.89 | 100
268 | 9 | 2018-03-26 | 89 | 1235 | 7007 A Patrick Place #1235 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
269 | 10 | 2018-03-26 | 89 | 1236 | 7007 B Patrick Place #1236 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
270 | 11 | 2018-03-26 | 89 | 1237 | 7007 C Patrick Place #1237 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
271 | 12 | 2018-03-26 | 89 | 1238 | 7007 D Patrick Place #1238 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
272 | 13 | 2018-03-26 | 89 | 1239 | 7013 A Patrick Place #1239 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
273 | 14 | 2018-03-26 | 89 | 1240 | 7013 B Patrick Place #1240 | Lincoln | Add conn. & app. | A | [8 empty] | 7544.83 | 1774.06 | 7544.83 | 1774.06 | 9318.89 | 0 | 9318.89 | 100
274 | 15 | 2018-03-26 | 89 | 1241 | 7013 C Patrick Place #1241 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
275 | 16 | 2018-03-26 | 89 | 1242 | 7013 D Patrick Place #1242 | Lincoln | Add conn. & app. | A | [8 empty] | 7544.83 | 1774.06 | 7544.83 | 1774.06 | 9318.89 | 0 | 9318.89 | 100
276
277 | 1 | 2018-04-02 | 89 | 1243 | 7019 A Patrick Place #1243 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
278 | 2 |  | 89 | 1244 | 7019 B Patrick Place #1244 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
279 | 3 | 2018-04-02 | 89 | 1245 | 7019 C Patrick Place #1245 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
280 | 4 | 2018-04-02 | 89 | 1246 | 7019 D Patrick Place #1246 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
281 | 5 | 2018-04-02 | 90 | 1247 | 7831 Carlton Arms Dr #1247 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
282 | 6 | 2018-04-02 | 90 | 1248 | 7833 Carlton Arms Drive #1248 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
283 | 7 | 2018-04-02 | 90 | 1249 | 7835 Carlton Arms Dr #1249 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
284 | 8 | 2018-04-02 | 90 | 1250 | 7837 Carlton Arms Dr #1250 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
285 | 9 | 2018-04-02 | 90 | 1251 | 7839 Carlton Arms Dr #1251 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
286 | 10 | 2018-04-02 | 90 | 1252 | 7841 Carlton Arms Dr #1252 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
287 | 11 | 2018-04-02 | 90 | 1253 | 7843 Carlton Arms Dr #1253 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
288 | 12 | 2018-04-02 | 90 | 1254 | 7845 Carlton Arms Dr #1254 | Madison | Existing W/D in unit | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
289 | 13 | 2018-04-02 | 90 | 1255 | 7847 Carlton Arms Dr #1255 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
290 | 14 | 2018-04-02 | 90 | 1256 | 7849 Carlton Arms Dr #1256 | Jefferson II | Existing W/D in unit | A | [8 empty] | 8857.83 | 1774.06 | 8857.83 | 1774.06 | 10631.89 | 0 | 10631.89 | 100
291 | 15 | 2018-04-02 | 90 | 1257 | 7851 Carlton Arms Dr #1257 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
292 | 16 | 2018-04-02 | 90 | 1258 | 7853 Carlton Arms Dr #1258 | Madison | Add app. only | A | [8 empty] | 8570.83 | 1774.06 | 8570.83 | 1774.06 | 10344.89 | 0 | 10344.89 | 100
293
294 | 1 | 2018-04-09 | 50 | 643 | 7745 A Carlton Arms Dr #0643 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
295 | 2 | 2018-04-09 | 50 | 644 | 7745 B Carlton Arms Dr #0644 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
296 | 3 | 2018-04-09 | 50 | 645 | 7745 C Carlton Arms Dr #0645 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
297 | 4 | 2018-04-09 | 50 | 646 | 7745 D Carlton Arms Dr #0646 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
298 | 5 | 2018-04-09 | 50 | 647 | 7751 A Carlton Arms Dr #0647 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
299 | 6 | 2018-04-09 | 50 | 650 | 7751 D Carlton Arms Dr #0650 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
300 | 7 | 2018-04-09 | 50 | 655 | 7757 C Carlton Arms Dr #0655 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
301 | 8 | 2018-04-09 | 50 | 658 | 7757 F Carlton Arms Dr #0658 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
302 | 9 | 2018-04-09 | 50 | 659 | 7763 A Carlton Arms Dr #0659 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
303 | 10 | 2018-04-09 | 50 | 660 | 7763 B Carlton Arms Dr #0660 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
304 | 11 | 2018-04-09 | 50 | 661 | 7763 C Carlton Arms Dr #0661 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
305 | 12 | 2018-04-09 | 50 | 662 | 7763 D Carlton Arms Dr #0662 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
306 | 13 | 2018-04-09 | 51 | 663 | 7010 A Old House Rd #0663 | Presidential | Add conn. & app. | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
307 | 14 | 2018-04-09 | 51 | 664 | 7010 B Old House Rd #0664 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
308 | 15 | 2018-04-09 | 51 | 665 | 7010 C Old House Road #0665 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
309 | 16 | 2018-04-09 | 51 | 666 | 7010 D Old House Rd #0666 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
310
311 | 1 | 2018-04-16 | 51 | 667 | 7016 A Old House Road #0667 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
312 | 2 | 2018-04-16 | 51 | 668 | 7016 B Old House Road #0668 | Presidential | Add conn. & app. | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
313 | 3 | 2018-04-16 | 51 | 669 | 7016 C Old House Rd #0669 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
314 | 4 | 2018-04-16 | 51 | 670 | 7016 D Old House Rd #0670 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
315 | 5 | 2018-04-16 | 51 | 671 | 7022 A Old House Road #0671 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
316 |  |  | 51 | 672 | 7022 B Old House Road #0672 | Gettysburg | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
317 | 6 | 2018-04-16 | 51 | 673 | 7022 C Old House Road #0673 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
318 | 7 | 2018-04-16 | 51 | 674 | 7022 D Old House Road #0674 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
319 | 8 | 2018-04-16 | 51 | 675 | 7028 A Old House Road #0675 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
320 | 9 | 2018-04-16 | 51 | 676 | 7028 B Old House Road #0676 | Presidential | Existing W/D in unit | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
321 | 10 | 2018-04-16 | 51 | 677 | 7028 C Old House Road #0677 | Gettysburg | Add conn. & app. | A | [8 empty] | 8562.83 | 1774.06 | 8562.83 | 1774.06 | 10336.89 | 0 | 10336.89 | 100
322 | 11 | 2018-04-16 | 51 | 678 | 7028 D Old House Road #0678 | Presidential | Add app. only | A | [8 empty] | 9096.83 | 1774.06 | 9096.83 | 1774.06 | 10870.89 | 0 | 10870.89 | 100
323 | 12 | 2018-04-16 | 13 | 139 | 7711 A Newport Way #0139 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
324 |  |  | 13 | 140 | 7711 B Newport Way #0140 | Harrison II | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
325 | 13 | 2018-04-16 | 13 | 141 | 7711 C Newport Way #0141 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
326 | 14 | 2018-04-16 | 13 | 142 | 7711 D Newport Way #0142 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
327 | 15 | 2018-04-16 | 13 | 143 | 7717 A Newport Way #0143 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
328 | 16 | 2018-04-16 | 13 | 146 | 7717 D Newport Way #0146 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
329
330 | 1 | 2018-04-23 | 13 | 151 | 7723 C Newport Way #0151 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
331 | 2 | 2018-04-23 | 13 | 154 | 7723 F Newport Way #0154 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
332 | 3 | 2018-04-23 | 13 | 155 | 7729 A Newport Way #0155 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
333 | 4 | 2018-04-23 | 13 | 156 | 7729 B Newport Way #0156 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
334 | 5 | 2018-04-23 | 13 | 157 | 7729 C Newport Way #0157 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
335 | 6 | 2018-04-23 | 13 | 158 | 7729 D Newport Way #0158 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
336 | 7 | 2018-04-23 | 14 | 167 | 7121 A Old House Rd #0167 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
337 | 8 | 2018-04-23 | 14 | 170 | 7121 D Old House Rd #0170 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
338 | 9 | 2018-04-23 | 15 | 181 | 7145 A Old House Rd #0181 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
339 | 10 | 2018-04-23 | 15 | 182 | 7145 B Old House Rd #0182 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
340 | 11 | 2018-04-23 | 15 | 183 | 7145 C Old House Rd #0183 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
341 | 12 | 2018-04-23 | 15 | 184 | 7145 D Old House Rd #0184 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
342 | 13 | 2018-04-23 | 15 | 185 | 7151 A Old House Rd #0185 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
343 |  |  | 15 | 186 | 7151 B Old House Rd #0186 | Constitution | No renovation | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
344 | 14 | 2018-04-23 | 15 | 187 | 7151 C Old House Rd #0187 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
345 | 15 | 2018-04-23 | 15 | 188 | 7151 D Old House Rd #0188 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
346 | 16 | 2018-04-23 | 15 | 189 | 7157 A Old House Rd #0189 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
347
348 | 1 | 2018-04-30 | 15 | 190 | 7157 B Old House Rd #0190 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
349 | 2 | 2018-04-30 | 15 | 191 | 7157 C Old House Rd #0191 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
350 | 3 | 2018-04-30 | 15 | 192 | 7157 D Old House Rd #0192 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
351 | 4 | 2018-04-30 | 15 | 193 | 7163 A Old House Rd #0193 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
352 | 5 | 2018-04-30 | 15 | 194 | 7163 B Old House Rd #0194 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
353 | 6 | 2018-04-30 | 15 | 195 | 7163 C Old House Rd #0195 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
354 | 7 | 2018-04-30 | 15 | 196 | 7163 D Old House Rd #0196 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
355 | 8 | 2018-04-30 | 16 | 205 | 7722 A Carlton Arms Rd #0205 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
356 | 9 | 2018-04-30 | 16 | 208 | 7722 D Carlton Arms Rd #0208 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
357 | 10 | 2018-04-30 | 17 | 219 | 7144 A American Way #0219 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
358 | 11 | 2018-04-30 | 17 | 220 | 7144 B American Way #0220 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
359 | 12 | 2018-04-30 | 17 | 221 | 7144 C American Way #0221 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
360 | 13 | 2018-04-30 | 17 | 222 | 7144 D American Way #0222 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
361 | 14 | 2018-04-30 | 17 | 223 | 7150 A American Way #0223 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
362 | 15 | 2018-04-30 | 17 | 224 | 7150 B American Way #0224 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
363 | 16 | 2018-04-30 | 17 | 225 | 7150 C American Way #0225 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
364
365 | 1 | 2018-05-07 | 17 | 226 | 7150 D American Way #0226 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
366 | 2 | 2018-05-07 | 17 | 227 | 7156 A American Way #0227 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
367 | 3 | 2018-05-07 | 17 | 228 | 7156 B American Way #0228 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
368 | 4 | 2018-05-07 | 17 | 229 | 7156 C American Way #0229 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
369 | 5 | 2018-05-07 | 17 | 230 | 7156 D American Way #0230 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
370 | 6 | 2018-05-07 | 17 | 232 | 7162 B American Way #0232 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
371 | 7 | 2018-05-07 | 17 | 233 | 7162 C American Way #0233 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
372 | 8 | 2018-05-07 | 17 | 234 | 7162 D American Way #0234 | Constitution | Add conn. & app. | A | [8 empty] | 8478.83 | 1774.06 | 8478.83 | 1774.06 | 10252.89 | 0 | 10252.89 | 100
373 | 9 | 2018-05-07 | 18 | 235 | 7118 a American Way #0235 | Liberty | Existing W/D in unit | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
374 | 10 | 2018-05-07 | 18 | 236 | 7118 B American Way #0236 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
375 | 11 | 2018-05-07 | 18 | 237 | 7118 C American Way #0237 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
376 | 12 | 2018-05-07 | 18 | 238 | 7118 D American Way #0238 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
377 | 13 | 2018-05-07 | 18 | 239 | 7124 A American Way #0239 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
378 | 14 | 2018-05-07 | 18 | 240 | 7124 B American Way #0240 | Lincoln | Existing W/D in unit | A | [8 empty] | 7544.83 | 1774.06 | 7544.83 | 1774.06 | 9318.89 | 0 | 9318.89 | 100
379 | 15 | 2018-05-07 | 18 | 241 | 7124 C American Way #0241 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
380 | 16 | 2018-05-07 | 18 | 242 | 7124 D American Way #0242 | Lincoln | Add conn. & app. | A | [8 empty] | 7544.83 | 1774.06 | 7544.83 | 1774.06 | 9318.89 | 0 | 9318.89 | 100
381
382 | 1 | 2018-05-14 | 18 | 243 | 7130 A American Way #0243 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
383 | 2 | 2018-05-14 | 18 | 244 | 7130 B American Way #0244 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
384 | 3 | 2018-05-14 | 18 | 245 | 7130 C American Way #0245 | Hancock II | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
385 | 4 | 2018-05-14 | 18 | 246 | 7130 D American Way #0246 | Liberty | Add conn. & app. | A | [8 empty] | 10056.83 | 1929.213 | 10056.83 | 1929.213 | 11986.043 | 0 | 11986.043 | 100
386 | 5 | 2018-05-14 | 85 | 1183 | 7048 A Patrick Place #1183 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
387 | 6 | 2018-05-14 | 85 | 1184 | 7048 B Patrick Place #1184 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
388 | 7 | 2018-05-14 | 85 | 1185 | 7048 C Patrick Place #1185 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
389 | 8 | 2018-05-14 | 85 | 1186 | 7048 D Patrick Place #1186 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
390 | 9 | 2018-05-14 | 85 | 1189 | 7054 C Patrick Place #1189 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
391 | 10 | 2018-05-14 | 85 | 1192 | 7054 F Patrick Place #1192 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
392 | 11 | 2018-05-14 | 85 | 1193 | 7060 A Patrick Place #1193 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
393 | 12 | 2018-05-14 | 85 | 1196 | 7060 D Patrick Place #1196 | Declaration | Add conn. & app. | A | [8 empty] | 8209.83 | 1929.21 | 8209.83 | 1929.21 | 10139.04 | 0 | 10139.04 | 100
394 | 13 | 2018-05-14 | 85 | 1199 | 7066 A Patrick Place #1199 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
395 | 14 | 2018-05-14 | 85 | 1200 | 7066 B Patrick Place #1200 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
396 | 15 | 2018-05-14 | 85 | 1201 | 7066 C Patrick Place #1201 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
397 | 16 | 2018-05-14 | 85 | 1202 | 7066 D Patrick Place #1202 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
398
399 | 1 | 2018-05-21 | 81 | 1129 | 7017 A Caisson Street #1129 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
400 | 2 | 2018-05-21 | 81 | 1132 | 7017 D Caisson Street #1132 | Hancock | Add conn. & app. | A | [8 empty] | 7551.83 | 1774.06 | 7551.83 | 1774.06 | 9325.89 | 0 | 9325.89 | 100
401 | 3 | 2018-05-21 | 82 | 1143 | 7925 A Carlton Arms Dr #1143 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
402 | 4 | 2018-05-21 | 82 | 1144 | 7925 B Carlton Arms Dr #1144 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
403 | 5 | 2018-05-21 | 82 | 1145 | 7925 C Carlton Arms Dr #1145 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
404 | 6 | 2018-05-21 | 82 | 1146 | 7925 D Carlton Arms Dr #1146 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
405 | 7 | 2018-05-21 | 82 | 1147 | 7931 A Carlton Arms Dr #1147 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
406 | 8 | 2018-05-21 | 82 | 1148 | 7931 B Carlton Arms Dr #1148 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
407 | 9 | 2018-05-21 | 82 | 1149 | 7931 C Carlton Arms Dr #1149 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
408 | 10 | 2018-05-21 | 82 | 1150 | 7931 D Carlton Arms Dr #1150 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
409 | 11 | 2018-05-21 | 82 | 1151 | 7937 A Carlton Arms Dr #1151 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
410 | 12 | 2018-05-21 | 82 | 1152 | 7937 B Carlton Arms Dr #1152 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
411 | 13 | 2018-05-21 | 82 | 1153 | 7937 C Carlton Arms Dr #1153 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
412 | 14 | 2018-05-21 | 82 | 1154 | 7937 D Carlton Arms Dr #1154 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
413 | 15 | 2018-05-21 | 82 | 1155 | 7943 A Carlton Arms Dr #1155 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
414 | 16 | 2018-05-21 | 82 | 1156 | 7943 B Carlton Arms Dr #1156 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
415
416 | 1 | 2018-05-28 | 82 | 1157 | 7943 C Carlton Arms Dr #1157 | Patriot | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
417 | 2 | 2018-05-28 | 82 | 1158 | 7943 D Carlton Arms Dr #1158 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
418 | 3 | 2018-05-28 | 83 | 1159 | 7909 A Carlton Arms Dr #1159 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
419 | 4 | 2018-05-28 | 83 | 1160 | 7909 B Carlton Arms Dr #1160 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
420 | 5 | 2018-05-28 | 83 | 1161 | 7909 C Carlton Arms Dr #1161 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
421 | 6 | 2018-05-28 | 83 | 1162 | 7909 D Carlton Arms Dr #1162 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
422 | 7 | 2018-05-28 | 83 | 1163 | 7915 A Carlton Arms Dr #1163 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
423 | 8 | 2018-05-28 | 83 | 1164 | 7915 B Carlton Arms Dr #1164 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
424
425 | 1 | 2018-06-04 | 83 | 1165 | 7915 C Carlton Arms Dr #1165 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
426 | 2 | 2018-06-04 | 83 | 1166 | 7915 D Carlton Arms Dr #1166 | Washington I | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
427 | 3 | 2018-06-04 | 83 | 1167 | 7921 A Carlton Arms Dr #1167 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
428 | 4 | 2018-06-04 | 83 | 1168 | 7921 B Carlton Arms Dr #1168 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
429 | 5 | 2018-06-04 | 83 | 1169 | 7921 C Carlton Arms Dr #1169 | Washington III | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
430 | 6 | 2018-06-04 | 83 | 1170 | 7921 D Carlton Arms Dr #1170 | Washington II | Add conn. & app. | A | [8 empty] | 7891.83 | 1774.06 | 7891.83 | 1774.06 | 9665.89 | 0 | 9665.89 | 100
431 | 7 | 2018-06-04 | 6 | 63 | 7022 A American Way #0063 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
432 | 8 | 2018-06-04 | 6 | 64 | 7022 B American Way #0064 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
433 | 9 | 2018-06-04 | 6 | 65 | 7022 C American Way #0065 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
434 | 10 | 2018-06-04 | 6 | 66 | 7022 D American Way #0066 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
435 | 11 | 2018-06-04 | 6 | 67 | 7028 A American Way #0067 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
436 | 12 | 2018-06-04 | 6 | 68 | 7028 B American Way #0068 | Independence | Existing W/D in unit | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
437 | 13 | 2018-06-04 | 6 | 69 | 7028 C American Way #0069 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
438 | 14 | 2018-06-04 | 6 | 70 | 7028 D American Way #0070 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
439 | 15 | 2018-06-04 | 7 | 71 | 7715 A Carlton Arms Drive # 0071 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
440 | 16 | 2018-06-04 | 7 | 72 | 7715 B Carlton Arms Drive # 0072 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
441
442 | 1 | 2018-06-11 | 7 | 73 | 7715 C Carlton Arms Drive # 0073 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
443 | 2 | 2018-06-11 | 7 | 74 | 7715 D Carlton Arms Drive #74 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
444 | 3 | 2018-06-11 | 7 | 75 | 7721 A Carlton Arms Dr #75 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
445 | 4 | 2018-06-11 | 7 | 76 | 7721 B Carlton Arms Drive #76 | Independence | Add app. only | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
446 | 5 | 2018-06-11 | 7 | 77 | 7721 C Carlton Arms Drive #77 | Harrison I | Existing W/D in unit | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
447 | 6 | 2018-06-11 | 7 | 78 | 7721 D Carlton Arms Dr. #78 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
448 | 7 | 2018-06-11 | 10 | 103 | 7011 A Old House Road #103 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
449 | 8 | 2018-06-11 | 10 | 104 | 7011 B Old House Road#0104 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
450 | 9 | 2018-06-11 | 10 | 105 | 7011 C Old House Rd #0105 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
451 | 10 | 2018-06-11 | 10 | 106 | 7011 D Old House Rd #0106 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
452 | 11 | 2018-06-11 | 10 | 107 | 7017 A Old House Rd #0107 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
453 | 12 | 2018-06-11 | 10 | 110 | 7017 D Old House Rd #0110 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
454 | 13 | 2018-06-11 | 10 | 115 | 7023 C Old House Rd #0115 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
455 | 14 | 2018-06-11 | 10 | 118 | 7023 F Old House Rd #0118 | Patriot II | Add conn. & app. | A | [8 empty] | 8752.83 | 1929.21 | 8752.83 | 1929.21 | 10682.04 | 0 | 10682.04 | 100
456 | 15 | 2018-06-11 | 10 | 119 | 7029 A Old House Rd #0119 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
457 | 16 | 2018-06-11 | 10 | 120 | 7029 B Old House Rd #0120 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
458
459 | 1 | 2018-06-18 | 10 | 121 | 7029 C Old House Rd #0121 | Harrison II | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
460 | 2 | 2018-06-18 | 11 | 123 | 7712 A Newport Way #0123 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
461 | 3 | 2018-06-18 | 11 | 124 | 7712 B Newport Way #0124 | Independence | Add app. only | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
462 | 4 | 2018-06-18 | 11 | 125 | 7712 C Newport Way #0125 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
463 | 5 | 2018-06-18 | 11 | 126 | 7712 D Newport Way #0126 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
464 | 6 | 2018-06-18 | 11 | 127 | 7718 A Newport Way #0127 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
465 | 7 | 2018-06-18 | 11 | 128 | 7718 B Newport Way #0128 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
466 | 8 | 2018-06-18 | 11 | 129 | 7718 C Newport Way #0129 | Independence | Add conn. & app. | A | [8 empty] | 8467.83 | 1774.06 | 8467.83 | 1774.06 | 10241.89 | 0 | 10241.89 | 100
467 | 9 | 2018-06-18 | 11 | 130 | 7718 D Newport Way #0130 | Harrison I | Add conn. & app. | A | [8 empty] | 7856.83 | 1774.06 | 7856.83 | 1774.06 | 9630.89 | 0 | 9630.89 | 100
END OF PHASE I ROLLOUT
3466669.76