Triple Helix-konseptet

Internationally, the symbolics of Triple Helix (taken from mathematic models in DNA research) has been introduced in the description of symbiosis processes within innovation – illustrating how organisms may interact with each othe, ifluence on and change each others behavior. From the link below, the following statements have been extracted:

http://www.triplehelixconference.org/the-triple-helix-concept.html

The triple Helix concept comprises three basic elements: (1) a more prominent role for the university in innovation, on a par with industry and government in a knowledge based society; (2) a movement toward collaborative relationship among the three major institutional spheres, in which innovation policy is increasingly an outcome of interaction rather than a prescription from government; (3) in addition to fulfilling their traditional functions, each institutional sphere also “takes the role of the other” performing new roles as well as their non-traditional function. Institutions taking non-traditional roles are viewed as major potential source of “innovation in innovation”.

InnoVat

Innovation and Etrepreneurship for Work Life

A Nordic-Baltic cooperative project on the development of innovation and entrepreneurship in a symbiosis between education, trade/industry and governmental organisations.

Application to the NORDPLUS program: NORDPLUS Horizontal, through “Norwegian Centre for International Cooperation in education, SiU”

(Application sumitted: 1st March	Answer: 1st June)

InnoVat – Prosject activities – Prosject language: English

The project tasks will be subdevided into the following WorkPackages – WPs

WP 01: Project administration, process- and economic control, information and reporting.

WP 02: Development and support of the project web-portal

WP 03:	Analysis and development of the concept “Innovation and Entrepreneurship” (IE) within the partner institutions and the work practice within the involved innovation centres. Cooperation with trade/industry and governmental organisations through innovation centres or corresponding organisations for channeling contact with work life. Development of differentiated courses within IE – and testing of these.

WP 04:Dissemination of project results and experiences. Producing printed material on project results and experiences, presentation of results at international conferences. Concluding international conference on IE in Trysil early summer 2014.

WP 05: Evaluation