## UI Design Backlog
Product Backlog | [9 empty] | Estimated total | 211
[5 empty] | Feature / Bug / Doc / Admin |  |  |  | 1/2/4/8 or multiples | 1/2/4/8 or multiples
Group | Group Type | Task | Description | Revision | Type | Issues | Resolutions | Owner | Actual hours | Estimated | Money | SubTotal | Day allocated | Day#Task | Sprint | Target version | Final version
Screen 2: Edit Investment | Screen | Screen UI | Backlog line #19 – tap photo on screen #2 and screen #3 opens – described elsewhere. Stay on screen #2 by swiping left/right to see more photos. • Store links of photos from Zillow and google on server. Store photo and link on user device. | 2 | Feature | [6 empty] | 0 |  | #Screen 2: Edit Investment | 3 | 1.0 - Prop Details
Screen 2: Edit Investment | Screen | Tap 3,6,9 | # Profit gets updated for 3,6,9 months # Remodel Budget "i" drops Remodel budget down or closes it # Soft Costs "i" drops Soft costs or closes it | 2 | Feature | [6 empty] | 0 |  | #Screen 2: Edit Investment | 3 | 1.0 - Prop Details
Screen 2: Edit Investment | Screen | Share button | # upper right corner: prepares a html e-mail with a PDF attached, describing this deal | 2 | Feature | [6 empty] | 0 |  | #Screen 2: Edit Investment | 3 | 1.0 - Prop Details
Screen 2: Edit Investment | Screen | Share button | # upper right corner: shares the deal to a third party # the app generates a html email with all the details and an attachment (".flipdecider" file) # the 3rd party can interact with the deal on their iPhone # 3rd party downloads the app and interacts with the ".flipdecider" file # the deal i shared one way only # pictures are shared with the server (made smaller, then posted to the server). The server generates an URL with these pictures and they get downloaded if needed by the destination user # the new user can use the suggested title for new imported investment: address + " " + originator | 2 | Feature | next version | [5 empty] | 0 |  | #Screen 2: Edit Investment | 3 | 1.0 - Prop Details
Screen 5: Review Property Data | Screen | Screen UI | [new] #5 Add -import Photo from Google, Save to photo to photo gallery [new] # if not available, the screen shows a default picture [new] Access from screen #5 – icon on corner of the google photo -> tap on picture takes user to Standard Map View -> Aerial View -> Hybrid View (Screen 6D) # the user reviews the info from the PR(P) for that property # the user can change all entries here # Bed, Baths, Garages affect remodel budget # Sqft affects Remodel budget # Tax is an input for Holding costs # owner information is not available # if there is no Internet access or no PR(P) access, the user sees empty cells instead of the PR(P) properties pulled from the web # the user should be able to enter data in all cells (except Owner info) | 2 | Feature | [6 empty] | 0 |  | #Screen 5: Review Property Data | 3 | 1.0 - Prop Details
Screen 5: Review Property Data | Screen | Comparables | # the user taps a button to pull the PR(P) comparables for that address and navigates to the comparables screen #6 # if there is no internet access or no PR(P) data available the comparables screen will show only the target address | 2 | Feature | [6 empty] | 0 |  | #Screen 5: Review Property Data | 3 | 1.0 - Prop Details
Screen 5: Review Property Data | Screen | Send postcard button | # need third party supplier for Owner information API (if the owner information exists, enable the send postcard button) # Owner information is not available by default (see postcard) | 2 | Feature | [6 empty] | 0 |  | #Screen 5: Review Property Data | 3 | 1.0 - Prop Details
Screen 6: Comparables | Screen | Reload | • a reload button allows the user to reload comparables for the MLSID representing his investment; present a warning message that all saved comparables will be lost • Segmented view: Active, Opt/ Contract, Sold (can be activated individually) filters the comparables based on their status. An MLSID can have only one status | 2 | Feature | all past comparables and their options are lost | [5 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6: Comparables | Screen | Details | # dynamic listings show for each property: main picture, price went up / down (arrow), property address, property price # Tapping on the listing will show more details on screen 6c | 2 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6: Comparables | Screen | ARV | # ARV is an average of checked listings # listings are checked and unchecked by tapping on the accesory view; unchecked listings are not used for the average ARV # Your ARV can be manually entered or can be populated with calculated ARV by tapping on down arrow | 2 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6: Comparables | Screen | List View | # long tap shows a menu to confirm delete of the listing [listings are stored by MLS ID] - an existing property has several MLS IDs saved as ARV comparables and target purchase price comparables | 2 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6: Comparables | Screen | Map View | # Segmented view: Active, Opt/ Contract, Sold (can be activated individually) - filter is the same as in List View # shows property on the map along with comparables | 2 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6: Comparables | Screen | Draw button | # draw button - once we're done drawing, the listings inside the drawn area are going to be checked, those outside of the area will be deleted | 2 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 4 | 3.0 - Comparables
Screen 6: Comparables | Screen | Pin | # shows complex pin view: property picture, condensed info (see 6C, Listing Detail), allows user to tap and navigate to 6C) | 3 | Feature | [6 empty] | 0 |  | #Screen 6: Comparables | 3 | 3.0 - Comparables
Screen 6c: Comparable Detail | Screen | Listing detail | # Show listing photos - swipe shows next photo # Show listing details: property overview, beds, baths, sqft, lot size, price, price / sqft, property type, year built, neighborhood, property status [see Realtor.com app) [data pulled from MLS by MLS ID or from Zillow by zpid] [new]- show picture gallery with left right swipe picture gallery [new] - checkbox - uncheck / check to include the property in average calculation - show property details ... (see above for list) | 3 | Feature | [6 empty] | 0 |  | #Screen 6c: Comparable Detail | 3 | 3.0 - Comparables
Screen 6c: Comparable Detail | Screen | Listing detail | Additional options available on this screen: [new]- my rating 5 stars [new] - notes edit box | 3 | Feature | [6 empty] | 0 |  | #Screen 6c: Comparable Detail | 3 | 3.0 - Comparables
Screen 6D: Map View | Screen | Screen UI | New screen 6D shows hybrid aerial view and map view (+street view only on Android) of property – no other buttons, searches or functions. # shows a standard map view by default # shows a two state segmented control: standard view / hybrid view (street view on Android) | 3 | Feature | [6 empty] | 0 |  | #Screen 6D: Map View | 3 | 1.0 - Prop Details
Screen 7: Search Filters | Screen | Screen UI | # provides a filter for each of the MLS comparable entries: filter items have a minimum and a maximum value; pool can be YES (with pool) or NO (without pool) # Status can have multiple values and tapping it will push screen #8 for user selection # hitting back from this screen will trigger a new MLS comparables refresh with the new conditions | 2 | Feature | [6 empty] | 0 |  | #Screen 7: Search Filters | 3 | 3.0 - Comparables
Screen 9: Remodel budget | Screen | Edit List | # tapping one of the categories will take the user to screen #10, allowing him to edit the category details | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9: Remodel budget | Screen | Totals | # shows a total from the remodel budget categories # guestimate is sqft * $ / sqft # a segment selection tool allows selection between the total and the guestimate for the remodel budget | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9: Remodel budget | Screen | $ / sqft selection | # default to $30 / ft # a +- tool allows the user to refine the number to a round number | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9: Remodel budget | Screen | Screen UI | # apply custom graphics elements | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9: Remodel budget | Screen | Initial | # when the user first accesses this screen after the investment was added, he will see: 1. the guestimate remodel budget and corresponding $ / sqft 2. Exterior - House, Exterior - Yard, General Remodel, Kitchen, Bathrooms, Permits (all with $0) Note: this way we ensure the remodel budget equals the big number selected initially | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9: Remodel budget | Screen | Edit | # allows the rearrangement of the existing categories (no delete) | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 9: Remodel budget | 3 | 4.0 - Costs
Screen 9A: Remodel budget - Add | Screen | Add | # adds a new category: define a name and notes for that category | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 9A: Remodel budget - Add | 3 | 4.0 - Costs
Screen 10: Remodel Category | Screen | Screen UI | # shows a static number of "projects" (e.g. roof, siding) predefined # shows custom user defined projects # also shows a Guestimate: e.g. $10,000 (it's a guestimate for the category # all budgets for projects add up to a Running total | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 10: Remodel Category | 3 | 4.0 - Costs
Screen 10: Remodel Category | Screen | Project detail | # each project has a measurement unit, number of units, price per unit and a budget (price / unit * units) # users can add notes to a project item directly on this screen # users cannot edit measurement unit ($ / unit is a resulting field) e.g. sqft => $/sqft for price description | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 10: Remodel Category | 3 | 4.0 - Costs
Screen 10: Remodel Category | Screen | Edit | # allows the user to rearrange projects and delete their own custom ones | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 10: Remodel Category | 3 | 4.0 - Costs
Screen 10: Remodel Category | Screen | Add | # Pushes screen #11 # if the user hits Save on screen #11 it adds a new empty project to the list of projects | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 10: Remodel Category | 3 | 4.0 - Costs
Screen 11: New Project | Screen | Suppliers | # show Suppliers per Project for default projects (category is the project name) | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 11: New Project | 3 | 4.0 - Costs
Screen 11: New Project | Screen | Screen UI | # allows the user to enter a project name; (once the project name is defined, it cannot be changed) # request measurement unit, this will be locked in the next screen # hitting Save will add a new project, navigating back will cancel the project [new] –Need details and fields from # 10. From screen #10, tap on right arrow to go to screen #11 to edit. (this screen will edit unit, $/unit, quantity and notes) | 2 | Feature |  |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 11: New Project | 3 | 4.0 - Costs
Screen 12: New Budget category | Screen | Screen UI | # Allows the user to define a new budget category along with examples of what should go into that category | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 12: New Budget category | 3 | 4.0 - Costs
Screen 13: Holding costs | Screen | Detailed View | #TableViewController with dynamic cells; cells will be loaded from a configuration file # except Tax: fixed line, fetching from Property Info (screen #5) [new] # Tax absolute value: Tax current appraised tax valuation info from tax (2013) (screen #5), [new] # Tax as % of valuation: or select to fill out ___%. Autofill to 1.2% of current appraised tax valuation (screen #5) User can change that ___%. [new] # Tax as % of purchase price: If no current appraised value available – calculate as ___% of purchase price. By default, purchase price is 0 if user did not select a price [new] # | 2 | Feature |  |  |  |  | 10 | 45 | 0 | 9 | 9#Screen 13: Holding costs | 3 | 4.0 - Costs
Screen 13: Holding costs | Screen | Add | # User should be able to add AND NAME for a new item (by default called other) # Once a user adds a new type of cost, we add a new “Other" line and so on | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 13: Holding costs | 3 | 4.0 - Costs
Screen 13: Holding costs | Screen | Screen UI | # Tapping an item opens screen 13A | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 13: Holding costs | 3 | 4.0 - Costs
Screen 13: Holding costs | Screen | Lenders | # Connect to Suppliers - Category: Lenders | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 13: Holding costs | 3 | 4.0 - Costs
Screen 13A: Holding costs edit | Screen | Item edit | # For a predefined cost item, the user enters the amount to be paid; - the name of the cost (item) cannot be changed, - notes can be changed (store notes along with the investment) all cost items are per month - user can choose another supplier - tapping "Contact supplie opens screen 22 | 2 | Feature |  |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 13A: Holding costs edit | 3 | 4.0 - Costs
Screen 13A: Holding costs edit | Screen | Edit Other | For the "other" item, the user can edit the name of the item and the notes | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 13A: Holding costs edit | 3 | 4.0 - Costs
Screen 14: Cost of Money | Screen | Screen UI | TableViewController with 3 static rows: 1st and 2nd Mortgage, Owner equity | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 14: Cost of Money | 3 | 5.0 - Cost of Money
Screen 14: Cost of Money | Screen | Screen UI | # slider chooses between 1-12 months - total / month gets updated | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 14: Cost of Money | 3 | 5.0 - Cost of Money
Screen 14: Cost of Money | Screen | Detailed View | # tap on 1st & 2nd Mortgage and owner equity pushes screen #15 and allows the user to edit that part # 2nd Mortgage lender screen is not available if not lender was selected for 1st Mortgage | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 14: Cost of Money | 3 | 5.0 - Cost of Money
Screen 14A: Lender | Screen | Choose 1st Mortgage lender | # shows a list of lenders chosen for 1st Mortgage for this investment # each lender has: max borrowed limit, interest rate, points (these settings are only available for this investment, and are taken from the lender notes in the supplier's screen) # there is a no lender option, if there is no need for a lender # user can edit lenders: delete / rearrange # user can pick a new lender: the suppliers screen is opened and pre-filtered for 1st Mortgage suppliers; a new lender is added to the lenders list with all fields 0 # when a user selects a lender that lender is checked and the old one is unchecked; its data points are added to the Money Costs screen; if the 2nd mortgage lender cannot "fit" into the 100% (2nd lender % = 100% - 1st % - owner equity%) then the 2nd lender is defaulted to "no lender" and the user is warned | 2 | Feature |  |  |  |  | 12 | 45 | 0 | 9 | 9#Screen 14A: Lender | 3 | 5.0 - Cost of Money
Screen 14A: Lender | Screen | Share deal | # [Send e-mail with entire deal PDF] sends the entire deal with “.flipdecider” file attached and the receiver can open the app and interact with the deal | 2 | Feature | next version |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 14A: Lender | 4 | 5.0 - Cost of Money
Screen 14B: Lender2 | Screen | Choose 2nd Mortgage lender | # if no lender was selected for 1st Mortgage, this screen is not accessible # shows a list of lenders chosen for 2nd Mortgage for this investment # each lender has: max borrowed limit for 2nd mortgage, interest rate, points (these settings are only available for this investment, and are taken from the lender notes in the supplier's screen) # there is a no lender option, if there is no need for a lender # user can edit lenders: delete / rearrange # user can pick a lender from the Suppliers screen: lender is added to the list with all fields 0 # when a user selects a lender, that lender is checked and the old one is unchecked # if a lender is selected, he needs to "fit" in the 100% total (e.g. if the 1st Mortgage has a 80% limit and 5% owner equity, this lender cannot lend more than 15%, but can lend less), if the lender does not "fit" he is disabled for selection; the accessory is still available, so the lender parameters can be edited and thus the lender re-enabled | 3 | Feature |  |  |  |  | 12 | 45 | 0 | 9 | 9#Screen 14B: Lender2 | 3 | 5.0 - Cost of Money
Screen 15: Mortgage Edit | Screen | Screen UI | # edit mortgage %, interest rate %, points %for a lender (owner equity only for 1st Mortgage lenders) # [Send e-mail with entire deal PDF] sends the entire deal with PDF attached (see edit investment screen #2) to the picked lender # [Contact lender button] Shows Lender contact details | 2 | Feature |  |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 15: Mortgage Edit | 3 | 5.0 - Cost of Money
Screen 16: Cost of Sale (CS) | Screen | Screen UI | #TableViewController with dynamic cells; cells will be loaded from a configuration file except tax # add homebuyer warranty | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 16: Cost of Sale (CS) | 3 | 4.0 - Costs
Screen 16: Cost of Sale (CS) | Screen | Edit | # when user taps on an a cost item, he can edit the item in screen 17 | 2 | Feature |  |  |  |  | 1 | 45 | 0 | 9 | 9#Screen 16: Cost of Sale (CS) | 3 | 4.0 - Costs
Screen 16: Cost of Sale (CS) | Screen | Add | # user can edit the "Other category" and add a new cost item | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 16: Cost of Sale (CS) | 3 | 4.0 - Costs
Screen 16: Cost of Sale (CS) | Screen | Suppliers | # [tap on on item] present the Suppliers screen for that particular cost item and the associated category: - default cost items have associated categories which are presented by default in the Suppliers screen (Suppliers screen with pre-defined filter) - user configured cost items will be connected to the full list of Suppliers (Suppliers screen with no filter) | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 16: Cost of Sale (CS) | 3 | 4.0 - Costs
Screen 17: Percent or $ | Screen | Screen UI | # requests a percentage OR a currency value for an element # this screen will be extended to accommodate handling of a guestimate for: - cost of money, cost of sale, holding costs | 2 | Feature | Warning: Once a hard coded $ amount was entered, the percentage is ignored. Any change in ARV price will not be reflected in the value of the item being edited here |  |  |  | 2 | 45 | 0 | 9 | 9#Screen 17: Percent or $ | 3 | 4.0 - Costs
Screen 18: Closing Cost to Purchase (CCP) | Screen | Screen UI | # Shows various closing costs; user can edit their fixed value or their percentage, same as with cost of sale | 2 | Feature | Warning: Once a hard coded $ amount was entered, the percentage is ignored. Any change in ARV price will not be reflected in the value of the item being edited here |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 18: Closing Cost to Purchase (CCP) | 3 | 4.0 - Costs
Screen 18: Closing Cost to Purchase (CCP) | Screen | Other | Allows the introduction of a new closing cost with: Name, fixed value or percent of purchase price), notes, supplier | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 18: Closing Cost to Purchase (CCP) | 3 | 4.0 - Costs
Screen 18A: Edit Item CCP | Screen | Edit item | # edits percent or value for a closing cost to purchase item # allows attaching of a supplier (tap "Pick another supplier) # shows the current supplier # tapping contact opens the supplier contact details | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 18A: Edit Item CCP | 3 | 4.0 - Costs
Screen 19-20: Contractors | Screen | Filtered | Filter by: 1. Category Appraisals / Money Lenders / etc. 2. Keywork: can be anything so you can span multiple categories 3. Name: useful for the user | 2 | Feature |  |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 19-20: Contractors | 3 | 6.0 - Contacts
Screen 19-20: Contractors | Screen | Screen UI | Shows a list of all contractors grouped by categories and sorted by votes. The same screen will be used to present a list of contractors for a specific task (e.g. Appraisal, or Lenders for screen #14). View can be filtered. | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 19-20: Contractors | 3 | 6.0 - Contacts
Screen 19-20: Contractors | Screen | Edit suppliers | # allows the user to rearrange suppliers under categories # allows the user to delete custom defined suppliers | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 19-20: Contractors | 3 | 6.0 - Contacts
Screen 19-20: Contractors | Screen | Add | Suppliers screen: when the user adds a new supplier, that supplier will be automatically pushed to the server. Its share status will be set to "share by default". FlipDecider will manually filter the suppliers and promote or push the top voted ones into the providers list. | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 19-20: Contractors | 3 | 6.0 - Contacts
Screen 19-20: Contractors | Screen | Votes Feedback | # user can vote for a supplier # if the supplier is custom defined by the user, the vote remains only in the user account and it is not shared with others (a user has a single vote per supplier) # if the supplier is a flipdecider.com supplier, then the vote is pushed online and the status is updated for other suppliers (average rating + number of votes) # 3 stars voting system for suppliers with feedback to the flipdecider.com server | 2 | Feature | # votes are associated by a user for a specific supplier |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 19-20: Contractors | 3 | 6.0 - Contacts
Screen 22: Contractor Contact | Screen | Screen UI | Shows contact details. Allows user to view / edit and add a new contact # contact have name, phone, e-mail, address and notes # a contacted can be called, e-mailed to, send meeting request # a contractor has ratings | 2 | Feature |  |  |  |  | 8 | 45 | 0 | 9 | 9#Screen 22: Contractor Contact | 4 | 6.0 - Contacts
Screen 22: Contractor Contact | Screen | Category | # a contractor has a category to which he belongs to; this is used by the filter function, when the contractor screen is displayed, or when the user wants to filter contractors by their role | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Screen 22: Contractor Contact | 4 | 6.0 - Contacts
Core Data Management | Server | Holding Costs | Holding costs will have predefined costs plus the ability to add new (NAMED) costs | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Core Data Management | 3 | 4.0 - Costs
Core Data Management | Server | Holding Costs | Holding costs can be paid monthly or yearly; when calculating monthly costs for 1,2,3 months, monthly costs are added to each month and yearly costs are added beginning with the 1st month, the 13 months and so on; Yearly costs cannot be prorated | 2 | Feature |  |  |  |  | 2 | 45 | 0 | 9 | 9#Core Data Management | 3 | 4.0 - Costs
Core Data Management | Server | Cost of Sale | Cost of Sale items have two values: a fixed amount and a percentage from the ARV price (Cost of sales items are paid once for each investment) | 2 | Feature |  |  |  |  | 4 | 45 | 0 | 9 | 9#Core Data Management | 3 | 4.0 - Costs
Postcard server | Server | Reallocation | • unused postcard sent jobs (say 2 of 5 where not sent yet), can be allocated to other jobs to extend them (e.g. 1 job has only 1 postcard, you can add 2 postcards to it) • the user does not need to pay an additional fee, nor can he allocate more than 5 sends per job, if postcards cannot be reallocated they will be sent by default • the user has the option to cancel sending postcards, but will lose the postcards and cannot reallocate them • once postcards have been sent, they cannot be reallocated | 2 | Feature | NEXT VERSION this way we avoid the unnecessary overhead of having to manage postcards long after they’ve been purchased |  |  |  | 16 | 45 | 0 | 9 | 9#Postcard server | 4 | 7.0 - Postcard reallocation
Postcard server | Server | Server API + UI | • add thumbnail photo from the device • update PDF link with photo | 2 | Feature | next version |  |  |  | 8 | 45 | 0 | 9 | 9#Postcard server | 4 | 7.0 - Postcard reallocation
Refer your friends | NotImplemented | TBD | I’d like to add a page for refer your friends. See https://www.dropbox.com/referrals Add with facebook, linkedin Post to facebook Tweet Search contact book. | 2 | Feature | [5 empty] | 45 | 0 | 9 | 9#Refer your friends | 5 | 5.0 - Cost of Money
Rentals | NotImplemented | TBD | MLS for rental comparables | 2 | Feature | TBD |  |  |  |  | 45 | 0 | 9 | 9#Rentals | 5 | 5.0 - Cost of Money
Sign contract papers | NotImplemented | TBD | Allows the user to generate documents needed for contract signing and receive them filled-in via e-mail | 2 | Feature | TBD |  |  |  |  | 45 | 0 | 9 | 9#Sign contract papers | 5 | 5.0 - Cost of Money
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3
[11 empty] | 0 | 0 | 9 | 9# | 3